## Sheet1
A-SIST PROJECT TIMELINE
In progress
Pending
Done
No | Activity | Status | Remarks | PIC | Deadline | Period
[6 empty] | Sep'16 | [29 empty] | Oct'16 | [30 empty] | Nov'16 | [29 empty] | Dec'16 | [30 empty] | Jan'17 | [30 empty] | Feb'17
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 | Login Module (keempat) | Done | Tinggal Signup | Tommy | 2016-09-04 | bar: Sep'16 4
2 | Database Job | Done | Update | Riko | 2016-09-04 | bar: Sep'16 4
3 | Modul Kedua(2) | Done |  |  | 2016-09-10
4 | Modul ketiga (3 Non Member) |  | Category |  | 2002-09-10 | Sep'16 1: 16
5 | Modul Kelima Sign Up (5 Job seeker)
6 | Modul keenam Sign Up (5.1 Employer)
7 | Modul SMS (6)
8 | Modul Home Logon Job Seeker N Employer (7)
9 | Modul Menu driver information (8)
10 | Modul Menu driver information Detail (8.1)
11 | Modul Job seeker N employer match (8.1.2)
12 | Modul Post Job (8.1.3)
13 | Modul Account Setting Menu (Job Seeker & Employer)
14 | Modul Profile Documentation (Job Seeker & Employer)
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52